## 00_Leeme
Vaultrum — Planilla de operación de Control de Calidad
Qué es | El registro operativo del Área de Control de Calidad: defectos, casos, regresión, verificación de build, riesgos, cobertura, gate y sesiones exploratorias.
Dónde vive esta copia | Plantilla vacía: 02_Agencia/Area control de calidad/Herramientas/ (se versiona, no se llena). Copia de trabajo: 06_Proyectos/<Proyecto>/06_Calidad/ (se llena, no se versiona).
Cuándo se crea la copia | Al abrir el primer QA de un proyecto. Se sigue usando en todos los siguientes: el registro de defectos es acumulativo, el QA es por épica.
Las filas EXAMPLE | Son ejemplos de formato. Se borran al empezar a operar.
Hoja | Qué registra y en qué paso se llena
Dashboard | Se calcula solo. No se escribe a mano.
Risk_Register | Paso 2 — Análisis de riesgo. Modos de falla concretos, no nombres de sistema.
Build_Verification | Paso 3 — Verificación de build. Una fila por build candidata. Decide si el pase empieza.
Test_Cases | Paso 4 — Pase de prueba. Casos dirigidos con su técnica, resultado y build.
Exploratory | Paso 4 — Sesiones exploratorias con charter, tiempo acotado y hallazgos.
Bugs | Paso 4 y 5 — Registro de defectos. Es la fuente de verdad; el QA sólo lleva el resumen.
Regression | Paso 5 — Qué comportamiento ya validado se protege, con qué criticidad y frecuencia.
Coverage | Paso 4 y 5 — Qué dimensiones se examinaron por requerimiento. Sin celdas vacías.
Release_Gate | Paso 5 — Criterios obligatorios del gate, con su evidencia y su estado.
References | Las prácticas públicas de las que sale cada mecanismo, y cómo se adaptó.
Las seis leyes de la verificación | Se miden con Herramientas/calidad.py sobre el QA instrumentado, y esta planilla es la evidencia.
Ley 1 — versión congelada | Build_Verification y la columna Build de cada hoja: nada se verifica sobre una build que puede cambiar.
Ley 2 — la build se acepta o se rechaza | Build_Verification: si un check bloqueante falla, el pase profundo no empieza.
Ley 3 — el hallazgo se reproduce | Bugs: Steps to Reproduce, Expected, Actual, Reproducibility y Evidence son obligatorios.
Ley 4 — nada se cierra sin reverificar | Bugs: Fix Build + Retest Result. Quien programa deja 'Ready for Retest'; cierra quien verificó.
Ley 5 — se declara lo no ejecutado | Coverage: sí / no / no aplica con razón. Una celda vacía es un hueco que nadie sabe que existe.
Ley 6 — riesgo aceptado con dueño | Release_Gate y Known Issues: cada desviación con impacto, dueño y aceptación escrita.
Los tres veredictos | GO: se cumplen los criterios de salida. CONDITIONAL GO: desviaciones enumeradas, con dueño y aceptación. NO-GO: condición obligatoria incumplida o evidencia insuficiente.
Regla | Nada sale de Control de Calidad por intuición. Sale por evidencia, riesgo conocido y una decisión explícita.

## Dashboard
Vaultrum — QA Operations Dashboard
KPI | Value | Severity | Open count | Gate / Usage | Rule
Total defects |  | Blocker |  | Build Intake | No QA execution without identifiable build/version.
Open defects |  | Critical |  | BVT / Smoke | If blocker smoke fails, stop the pass.
Open Blocker/Critical |  | Major |  | Functional QA | Execute risk-based coverage + negative/boundary testing.
Executed test cases |  | Minor |  | Regression | Mandatory on touched critical paths.
Test pass rate |  | Trivial |  | Retest | Fix is not closed until confirmed on target build.
Open release blockers |  |  |  | Release Gate | No-Go with unresolved mandatory criteria.
Recommended operating sequence | Output
1. Intake | Test basis + build + scope accepted
2. Risk review | Risk register / affected areas
3. BVT | Build accepted or rejected
4. Test pass | Cases + exploratory evidence
5. Triage | Defects prioritized and owned
6. Retest + regression | Fix confidence
7. Gate | Go / Conditional Go / No-Go

## Bugs
Defect Register
Bug ID | Title | Area / System | Build | Platform | Environment | Reporter | Date Found | Severity | Priority | Status | Reproducibility | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Evidence / Link | Owner | Root Cause Category | Fix Build | Retest Result | Regression Needed | Linked Requirement / Test | Days Open | Notes
BUG-EXAMPLE-001 | Example — item discarded without confirmation | Inventory | 0.9.4-dev | Windows | Release-like local build | QA | 2026-08-25 | Major | High | Open | Always | Inventory contains at least one item | 1) Open inventory 2) Drag item outside window 3) Release mouse | Discard confirmation is shown before removal | Item is removed immediately | video://example | Unassigned | Gameplay logic |  | Not Run | Yes | RQ-INV-014 / TC-INV-021 |  | EXAMPLE ROW — delete when starting a real project
Formulas:
Days Open = IF([Date Found]="","",IF([Status]="Closed",0,TODAY()-[Date Found]))

## Test_Cases
Test Case Repository
Test Case ID | Requirement / Feature | Area | Risk Level | Test Level | Test Type | Priority | Preconditions | Test Data | Steps | Expected Result | Platform | Automation | Automation ID | Last Build | Result | Linked Bugs | Owner | Evidence / Notes
TC-EXAMPLE-001 | RQ-INV-014 Discard item confirmation | Inventory | High | System | Functional / Negative | High | Inventory contains an item | Any discardable item | 1) Open inventory 2) Drag item outside 3) Release 4) Cancel popup 5) Repeat and confirm | Cancel preserves item; confirm removes exactly one item | Windows | Manual |  | 0.9.4-dev | Not Run |  | Unassigned | EXAMPLE ROW — derived from requirement, not from implementation

## Regression
Regression Suite
Regression ID | Test Case ID | System | Trigger / Change Type | Criticality | Frequency | Platform | Execution | Last Build | Last Result | Last Run | Owner | Notes
REG-EXAMPLE-001 | TC-EXAMPLE-001 | Inventory | Any inventory drag/drop change | High | Every candidate build | Windows | Manual | 0.9.4-dev | Not Run |  | Unassigned | EXAMPLE

## Build_Verification
Build Verification / Smoke Log
Build ID | Date | Branch / Commit | Platform | Tester | Install / Update | Launch | Main Menu | Core Loop | Save / Load | Critical Path | Crash / Freeze | Logs / Errors | Smoke Suite | Overall Result | Blocking Bug IDs | Evidence | Notes
0.9.4-dev | 2026-08-25 | develop / abc123 | Windows | QA | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Accepted |  | build://example | EXAMPLE

## Risk_Register
Quality Risk Register
Risk ID | Area / System | Failure Mode | Probability (1-5) | Impact (1-5) | Exposure | Detection Difficulty (1-5) | Priority Score | Player / Business Impact | Mitigation | Test Approach | Owner | Status | Notes
RISK-EXAMPLE-001 | Save System | Progress is corrupted after update | 3 | 5 |  | 4 |  | Permanent progress loss / release blocker | Versioned saves + migration + backups | Cross-version save compatibility matrix + destructive tests | Unassigned | Open | EXAMPLE

## Coverage
Requirement / Quality Coverage Matrix
Requirement ID | Feature / System | Risk | Linked Test Cases | Platforms | Happy Path | Negative | Boundary | State / Transition | Save / Load | Performance | Accessibility | Localization | Automation | Coverage Status | Notes
RQ-INV-014 | Inventory discard | High | TC-EXAMPLE-001 | Windows | Yes | Yes | Yes | Yes | N/A | N/A | Yes | N/A | Partial | Partial | EXAMPLE

## Release_Gate
Release / Process Quality Gate
Criterion | Category | Mandatory? | Evidence Source | Status | Blocking Defect / Risk | Owner | Notes
Candidate build uniquely identified and reproducible | Build | Yes | Build_Verification | Not Run
BVT / smoke suite passed | Build | Yes | Build_Verification | Not Run
No unresolved Blocker defects | Defects | Yes | Bugs | Not Run
No unresolved Critical defects without explicit waiver | Defects | Yes | Bugs | Not Run
Critical player path completed on target build | Functional | Yes | Test_Cases | Not Run
Touched critical systems regression passed | Regression | Yes | Regression | Not Run
Save/load and progression validated where applicable | Data Integrity | Yes | Test_Cases | Not Run
Target platform / configuration coverage completed | Compatibility | Yes | Coverage | Not Run
Performance budgets met or deviations approved | Performance | Yes | Evidence / profiler report | Not Run
Accessibility-critical interactions validated | Accessibility | Yes | Coverage | Not Run
Known issues reviewed and accepted | Release | Yes | Known issues / Bugs | Not Run
Evidence attached for mandatory checks | Auditability | Yes | All QA artifacts | Not Run
Go / Conditional Go / No-Go decision recorded | Governance | Yes | Gate report | Not Run

## Exploratory
Exploratory Test Sessions
Session ID | Charter / Mission | Build | Timebox (min) | Tester | Areas / Buckets | Setup / Data | Heuristics / Questions | Findings | Bug IDs | Coverage / Learning | Follow-up
EXP-EXAMPLE-001 | Explore inventory discard interactions while UI state changes | 0.9.4-dev | 45 | QA | Inventory + UI + Input | Full inventory, multiple item types | What happens when discard overlaps with close/open, drag, keyboard input, full inventory, scene transition? | Example findings |  | Covered interaction combinations not represented by scripted cases | Convert reproducible failures into defect + regression case

## References
Professional References Used for the QA Area
Organization / Source | Practice extracted | Vaultrum adoption | URL
Bungie — Testing with Building Blocks (GDC 2023) | Reusable testing buckets/components; combine for directed ad-hoc, planning/costing and live investigation; preserve reusable creations. | Reusable system test models + risk/vulnerability-based planning + exploratory charters. | https://gdcvault.com/play/1028865/Testing-with-Building-Blocks-A
Guerrilla Games — Horizon Zero Dawn QA case study (GDC 2018) | Early QA engagement, communication, risk management, test strategy, tools, telemetry and post-launch support. | QA participates upstream but remains a final independent quality gate. | https://gdcvault.com/play/1025153/-Horizon-Zero-Dawn-A
Riot Games — Automated Testing for League of Legends | CI build verification, blocker/core test sets, staged trust for automated tests, automated reporting/ticketing; manual destructive testing remains necessary. | BVT blocker gate + regression automation + flaky-test quarantine. | https://www.riotgames.com/en/news/automated-testing-league-legends
Santa Monica Studio — TestMonkey (GDC 2023) | Local/remote automated testing integrated with CI; visual, smoke, sanitizer, determinism, gameplay and code-integration suites. | Separate suites by purpose; central results dashboard. | https://sms.playstation.com/stories/gdc-2023-presentations/media/997
Square Enix — FFVII Remake QA automation (GDC 2021) | Replay/exploration automation to extend traversal/coverage; automation as force multiplier rather than substitute for judgment. | Automate repeatable/high-scale checks; preserve human exploratory testing. | https://www.gdcvault.com/play/1027355/-Final-Fantasy-VII-Remake
Xbox Certification | Clean release build, submission checks, BVT before full test pass, explicit test cases/expected results, configuration benches and final certification gate. | Formal intake -> BVT -> full pass -> release gate workflow. | https://learn.microsoft.com/en-us/gaming/game-publishing/concepts/certification/certification-guide
Valve Steamworks | Release checklist, testing branches, compatibility checklist and point-by-point review results. | Candidate branches + release-readiness checklist. | https://partner.steamgames.com/doc/store/testing
Unity Test Framework | Edit Mode, Play Mode and target-platform automated tests; performance test extension. | Technical automation layer for Unity projects, not the whole QA discipline. | https://docs.unity3d.com/6000.0/Documentation/Manual/testing-editortestsrunner.html